## Dashboard
OBU Autonomous Racing — Budget Tracker 2024/25
Formula SAE Cost Compliance Report ¦ Adapted from FIA Financial Regulations Framework
Total Budget | Total Actual | Headroom | Cap Utilisation
38680 | 41070 | -2390 | 106.2%
Season target spend | Year-to-date spend | Remaining budget | % of budget consumed
▸ CATEGORY BREAKDOWN
FIA-Mapped Category | Budget (£) | Actual (£) | Variance (£) | RAG | Root Cause Summary | Corrective Action Summary
Chassis & Aero Components | 11750 | 14200 | 2450 | RED | Largest variance: Monocoque / frame materials (CFRP pre-preg, core, consumable... | Introduce mandatory layup sign-off checklist. Maintain 10% CFRP material contingency....
Drivetrain & Suspension | 9200 | 8750 | -450 | GREEN | Largest variance: Steering rack, column & quick-release hub... | Qualify backup suppliers for all safety-critical steering components....
Manufacturing & Workshop | 6800 | 7600 | 800 | RED | Largest variance: CNC machine hire (uprights, brackets, pedal box — external s... | Lock CNC geometry sign-off to Week 8. Add £300 rework contingency to CNC budget....
Team Training & Development | 1100 | 1060 | -40 | GREEN | Largest variance: Coursera team subscriptions (CFD, FEA, data analysis — 4 mem... | Extend to 8 members in 2025/26. Require completion certificate as condition of membership....
Travel & Competition Logistics | 5200 | 5410 | 210 | AMBER | Largest variance: Van hire — Silverstone FS UK (3-day event, 7-seat + trailer)... | Book van minimum 4 months in advance. Obtain 3 quotes. Consider trailer-share agreement....
Testing & Shakedown | 3380 | 3100 | -280 | GREEN | Largest variance: Circuit hire — Silverstone MIRA test day (1 day, mid-season ... | Maintain consortium membership to retain access to discounted circuit testing....
Equipment & Tooling | 1250 | 950 | -300 | GREEN | Largest variance: Oscilloscope & multimeter (borrowed from university Elec Eng... | Renew loan agreement annually. Offer reciprocal support (e.g. data analysis help)....
TOTAL | 38680 | 41070 | 2390
▸ COMPLIANCE SUMMARY
Total Gross Overspend | 3460
Total Gross Savings | 1070
Net Variance | 2390
Categories RED | 2
Categories AMBER | 1
Categories GREEN | 4
Prepared by: Wolfgang Guio ¦ OBU Autonomous Racing ¦ 2024/25 Season ¦ Simulated data for portfolio purposes.

## Data
DATA INPUT SHEET — Edit blue cells only ¦ Sub-component detail feeds category totals automatically
Cat | # | Sub-Component / Line Item | FIA Category | Budget (£) | Actual (£) | RAG | Root Cause | Corrective Action
CH |  | ▸ Chassis & Aero Components |  | 11750 | 14200 | 2450 | 20.85% | RED
CH | 1 | Monocoque / frame materials (CFRP pre-preg, core, consumables) | Chassis & Aerodynamic Parts | 4800 | 6200 | RED | Layup failure in Week 6 required full re-lamination of monocoque tub. Additional pre-preg and vacuum bagging consumables added £1,400 above budget. | Introduce mandatory layup sign-off checklist. Maintain 10% CFRP material contingency.
CH | 2 | Aero package (front wing, diffuser, sidepods — outsourced laser cut & waterjet) | Chassis & Aerodynamic Parts | 3200 | 4500 | RED | Post-CFD correlation required endplate and diffuser geometry revision. Two additional outsourced laser-cut iterations added £1,300 in unbudgeted parts cost. | Freeze aero geometry at CFD sign-off gate (Week 4). Add aero iteration cost reserve.
CH | 3 | Bodywork & fairings (GRP moulds, paint, fixings) | Chassis & Aerodynamic Parts | 2100 | 1950 | GREEN | Bodywork produced in-house with university mould stock. Minor underspend on fixings. | Continue in-house production. Expand mould library for 2025/26 aero package.
CH | 4 | Structural adhesives, fasteners & chassis consumables | Chassis & Aerodynamic Parts | 900 | 820 | GREEN | Bulk adhesive order shared with another university team reduced per-unit cost. | Formalise inter-team procurement agreements for shared consumables.
CH | 5 | Safety cell / roll hoop (steel, welding materials) | Chassis & Aerodynamic Parts | 750 | 730 | GREEN | Roll hoop fabricated in-house by experienced welding lead. On budget. | Document fabrication procedure for knowledge transfer to next year's team.
DS |  | ▸ Drivetrain & Suspension |  | 9200 | 8750 | -450 | -4.891% | GREEN
DS | 1 | Engine & intake (Yamaha YZF-R6 sourced second-hand, seals, gaskets) | Listed Parts (Gearbox & Suspension) | 2800 | 2650 | GREEN | Second-hand engine sourced for £200 below budget. Gasket kit bought in bulk. | Maintain second-hand engine sourcing strategy. Document engine spec for next season.
DS | 2 | Gearbox internals & chain drive (sprockets, chain, bearings) | Listed Parts (Gearbox & Suspension) | 1400 | 1280 | GREEN | Chain and sprocket sourced via sponsor discount (15% off list price). | Expand sponsor framework to include drivetrain consumables category.
DS | 3 | Suspension wishbones & uprights (in-house CNC aluminium) | Listed Parts (Gearbox & Suspension) | 1800 | 1600 | GREEN | Wishbone brackets CNC-machined in-house, saving £320 vs outsource quote. | Document in-house vs outsource cost matrix. Apply model to other machined parts.
DS | 4 | Steering rack, column & quick-release hub | Listed Parts (Gearbox & Suspension) | 950 | 1050 | RED | Quick-release hub sourced from new supplier at higher price after original supplier stock-out. | Qualify backup suppliers for all safety-critical steering components.
DS | 5 | Wheel hubs, brake discs & callipers | Listed Parts (Gearbox & Suspension) | 1400 | 1350 | GREEN | Brake discs purchased as part of group buy with two other FSAE teams. | Continue group-buy strategy for standardised brake components.
DS | 6 | Differential & CV joints | Listed Parts (Gearbox & Suspension) | 850 | 820 | GREEN | CV joints reused from prior season car after inspection. Differential on budget. | Inspect and catalogue reusable drivetrain components at season end each year.
MF |  | ▸ Manufacturing & Workshop |  | 6800 | 7600 | 800 | 11.76% | RED
MF | 1 | CNC machine hire (uprights, brackets, pedal box — external supplier) | Manufacturing Operations | 2800 | 3300 | RED | Unplanned rework of upright geometry after simulation data review required two additional CNC sessions, adding £500 to hire cost. | Lock CNC geometry sign-off to Week 8. Add £300 rework contingency to CNC budget.
MF | 2 | 3D printing consumables (resin, FDM filament, post-processing) | Manufacturing Operations | 1200 | 1500 | RED | Resin prices rose 18% mid-season vs budget assumption. Additional iterations on brake duct prototypes added £150 in filament spend. | Review consumable pricing quarterly. Set per-part print approval threshold.
MF | 3 | Welding materials & gas (MIG/TIG — frame, exhaust, mounts) | Manufacturing Operations | 850 | 820 | GREEN | Gas consumption below estimate due to efficient joint preparation by welding lead. | Record gas usage per assembly stage for improved future budgeting.
MF | 4 | Workshop consumables (cutting discs, PPE, lubricants, sandpaper) | Manufacturing Operations | 600 | 580 | GREEN | Bulk PPE order at start of season reduced per-item cost. On budget. | Maintain bulk ordering strategy at season start.
MF | 5 | Outsourced waterjet & laser cutting (aero brackets, plates) | Manufacturing Operations | 950 | 980 | AMBER | Minor overspend on one additional laser-cut bracket iteration. Within tolerance. | Include one revision iteration in outsource budget estimate by default.
MF | 6 | Surface finish, anodising & powder coating (external) | Manufacturing Operations | 400 | 420 | AMBER | Anodising of uprights and hubs on budget. Slight overspend on powder coating. | Combine parts batches to reduce per-run powder coat cost.
TR |  | ▸ Team Training & Development |  | 1100 | 1060 | -40 | -3.636% | GREEN
TR | 1 | Coursera team subscriptions (CFD, FEA, data analysis — 24 members × 6 months) | Personnel (Capped Employees) | 480 | 480 | GREEN | Four team leads subscribed to Coursera for 6 months (£20/month each). Courses completed: FEA with Ansys, Python for Data Science, Vehicle Dynamics Fundamentals. | Extend to 8 members in 2025/26. Require completion certificate as condition of membership.
TR | 2 | Udemy licences (individual courses) | Personnel (Capped Employees) | 180 | 165 | GREEN | 7 targeted Udemy courses purchased at sale prices (avg £14 vs £25 list). Covered SolidWorks advanced surfacing, MATLAB/Simulink intro, and OpenFOAM basics. | Monitor Udemy sale cycles (typically Nov and Jan). Pre-identify courses in September.
TR | 3 | LinkedIn Learning team access (project management, presenting to sponsors) | Personnel (Capped Employees) | 120 | 120 | GREEN | University provided subsidised LinkedIn Learning access for 10 members. Sponsor presentation and project management modules completed by all senior members. | Leverage university learning platform deal annually. Add technical writing module.
TR | 5 | Internal workshop materials (printed guides, whiteboard supplies) | Personnel (Capped Employees) | 320 | 295 | GREEN | University printer used for most materials at subsidised cost. Minor underspend. | Continue using university printing facilities. Explore digital-first workshop format.
TL |  | ▸ Travel & Competition Logistics |  | 5200 | 5410 | 210 | 4.038% | AMBER
TL | 1 | Van hire — Silverstone FS UK (3-day event, 7-seat + trailer) | Travel & Freight | 900 | 1080 | RED | Van hire rate increased 15% vs prior year booking. No early reservation made. | Book van minimum 4 months in advance. Obtain 3 quotes. Consider trailer-share agreement.
TL | 2 | Van hire — FS Germany, Hockenheim (4-day, cross-channel) | Travel & Freight | 1400 | 1300 | GREEN | Cross-channel ferry discount granted £100. Diesel cost higher than budgeted. | Include 10% fuel and ferry contingency for all European events.
TL | 3 | Fuel costs (both events combined) | Travel & Freight | 600 | 590 | GREEN | Diesel prices rose significantly between budget-setting (Oct) and event dates (Jun/Jul). £180 overspend vs estimate. | Index fuel budget to HMRC advisory rates published in April each year.
TL | 4 | Team accommodation — FS UK (4 members × 2 nights) | Travel & Freight | 640 | 620 | GREEN | AirBnB near circuit booked early. Split cost with partner team for one night. | Continue early accommodation booking. Explore campsite options to further reduce cost.
TL | 5 | Team accommodation — FS Germany (4 members × 3 nights) | Travel & Freight | 880 | 870 | GREEN | Hostel booked 3 months in advance at student rate. On budget. | Maintain advance booking strategy for European events.
TL | 6 | Competition entry fees (FS UK + FS Germany) | Travel & Freight | 480 | 480 | GREEN | Entry fees paid at published rates. No change from prior year. | Budget at published rates. Apply for FSAE scholarship fund to offset entry costs.
TL | 7 | Freight / parts shipping (urgent courier for replacement parts mid-event) | Travel & Freight | 300 | 470 | RED | Upright failure at FS UK required emergency overnight courier of replacement part. £170 above budget. | Carry a spares kit for high-risk components. Build £200 emergency freight reserve.
TS |  | ▸ Testing & Shakedown |  | 3380 | 3100 | -280 | -8.284% | GREEN
TS | 1 | Circuit hire — Bicester (2 days, pre-season shakedown) | Testing & Track Operations | 1400 | 1200 | GREEN | One planned circuit day replaced by skidpad session at local airfield (free). Remaining day used for full dynamic envelope exploration. | Continue mixed-venue testing. Formalise airfield agreement with local landowner.
TS | 2 | Circuit hire — Silverstone MIRA test day (1 day, mid-season setup) | Testing & Track Operations | 800 | 800 | GREEN | MIRA test day secured via FSAE consortium discount. On budget. | Maintain consortium membership to retain access to discounted circuit testing.
TS | 3 | Tyres — test set (4 × Hoosier R25B, 13-inch) | Testing & Track Operations | 680 | 640 | GREEN | Tyre set purchased second-hand from retiring FSAE team. Good condition. | Establish second-hand tyre network via FSAE UK community forum.
TS | 4 | Data logging consumables (SD cards, USB cables, sensor wiring) | Testing & Track Operations | 220 | 195 | GREEN | Components sourced via student electronics discount. Minor underspend. | Maintain student discount registrations for electronics suppliers.
TS | 5 | Driver equipment hire (helmet, HANS, suit — event only) | Testing & Track Operations | 280 | 265 | GREEN | Helmet and HANS borrowed from university motorsport club store. Suit hired externally. | Invest in team-owned driver equipment set in 2025/26 to eliminate hire costs.
EQ |  | ▸ Equipment & Tooling |  | 1250 | 950 | -300 | -24% | GREEN
EQ | 1 | Oscilloscope & multimeter (borrowed from university Elec Eng dept) | Depreciation & Capital Equipment | 0 | 0 | N/A | Formalised loan agreement with Electrical Engineering department. Zero cost. | Renew loan agreement annually. Offer reciprocal support (e.g. data analysis help).
EQ | 2 | Data acquisition system (AiM Evo5 — borrowed from prior year team) | Depreciation & Capital Equipment | 0 | 0 | N/A | DAQ system retained from 2023/24 car. No replacement required. | Document DAQ condition at season end. Budget for replacement in 2026/27.
EQ | 3 | Tooling purchases — torque wrenches, drill bits, taps & dies | Depreciation & Capital Equipment | 850 | 620 | GREEN | Several tool purchases deferred as existing university workshop stock was sufficient. £230 underspend carried to contingency. | Conduct tool inventory audit at season start to avoid duplicate purchases.
EQ | 4 | Safety equipment — fire extinguisher refill, first aid kit top-up | Depreciation & Capital Equipment | 180 | 175 | GREEN | Extinguisher refill and first aid kit restocked at standard cost. On budget. | Schedule annual safety equipment audit in September at season start.
EQ | 5 | Workshop storage & organisation (shelving, labelled bins, cable management) | Depreciation & Capital Equipment | 220 | 155 | GREEN | Shelving units sourced second-hand. Cable management materials from university stores. | Photograph and document workshop organisation layout for handover to next committee.
|  | GRAND TOTAL |  | 38680 | 41070 | 2390

## Variance Analysis
VARIANCE ANALYSIS — Budget to Actual Decomposition
Category | Budget (£) | Actual (£) | Variance (£) | Var % | Budget Share %
Chassis & Aero Components | 11750 | 14200 | 2450 | 20.85% | 30.38%
Drivetrain & Suspension | 9200 | 8750 | -450 | -4.891% | 23.78%
Manufacturing & Workshop | 6800 | 7600 | 800 | 11.76% | 17.58%
Team Training & Development | 1100 | 1060 | -40 | -3.636% | 2.844%
Travel & Competition Logistics | 5200 | 5410 | 210 | 4.038% | 13.44%
Testing & Shakedown | 3380 | 3100 | -280 | -8.284% | 8.738%
Equipment & Tooling | 1250 | 950 | -300 | -24% | 3.232%
TOTAL | 38680 | 41070 | 2390 | 6.179% | 100%
▸ KEY VARIANCE METRICS
Worst Overspend Category | Chassis & Aero Components
Largest Saving Category | Drivetrain & Suspension
Total Gross Overspend | 3460
Total Gross Savings | 1070
Net Position | 2390
Biggest Overspend % (cats) | 20.85%

## Assumptions & Notes
ASSUMPTIONS, METHODOLOGY & NOTES
PURPOSE | Portfolio project demonstrating F1-style cost engineering methodology applied to a Formula SAE OBU team. Built to showcase variance analysis, FIA category mapping, and financial reporting skills for motorsport roles.
DATA SOURCE | All figures simulated. Sub-component breakdown reflects simulated Team cost available team reports and competition cost reports.
FIA MAPPING | Seven FIA Financial Regulation Article 2 categories adapted for university scale. Power Unit excluded per FIA convention. Driver compensation excluded (unpaid students). Category RAG auto-calculated from variance % thresholds: >5% = RED, 0–5% = AMBER, ≤0% = GREEN.
TRAINING | Team Training category uses online learning subscriptions (Coursera, Udemy, LinkedIn Learning) to reflect actual course subscription costs.
COLOUR CODE | Blue text = editable input. Black text = formula (do not edit). Yellow/amber = key output. RAG fills: Red/Amber/Green on status cells only.
HOW TO USE | 1. Go to Data sheet. 2. Edit blue cells (Budget, Actual, RAG, Root Cause, Corrective Action) for each sub-component. 3. Category totals update automatically. 4. Dashboard and Variance Analysis recalculate. 5. Do not edit formula cells (black text).
AUTHOR | Wolfgang Guio — MSc Motorsport Engineering (Distinction), Oxford Brookes University. LinkedIn: Wolfgang Guio ¦ GitHub: wguio07